## Overview
Rules Engine System Test and UAT Plan
Purpose | Provide a structured system test and UAT plan for validating the rules engine before deployment. The workbook supports technical execution, business acceptance, evidence capture, defect tracking, and release sign-off. | Metric | Value
Scope | Deployment setup notebooks, schema/table creation, standard function metadata registration, YAML compilation, semantic validation, Spark compatibility validation, publishing, version lifecycle, custom table names, function registry behavior, Python/Spark runtime evaluation, audit metadata, and business-facing UAT workflows. | System Tests Planned | 50
Out of Scope | Security penetration testing, production-scale load testing, downstream BI model certification, and domain-specific business rule design approval unless explicitly added by the project team. | UAT Tests Planned | 24
Primary Release Risk | Incorrect ruleset publication, function metadata setup, or runtime evaluation could assign wrong rule outcomes to business records or make production jobs load the wrong ruleset version. | Results Executed | 0
Entry Criteria | Package deployed to the test workspace, target catalog/schema is available or creatable, setup notebook exists, publish notebook exists, representative YAML rulesets are available, and testers can access Databricks job/notebook outputs. | Passed Results | 0
Exit Criteria | All Critical and High priority system tests pass, UAT sign-off is recorded, open defects have owner-approved disposition, and setup/publish notebooks are rerunnable in the target environment. | Open Defects | 0
Result Recording Standard | Each executed test should have a result, actual outcome, tester name, execution date, evidence location, and defect ID if the result is Fail or Blocked.
Recommended Evidence | Screenshots, notebook run URLs, job run URLs, table query results, exported row counts, or Databricks cell outputs that show the observed result.

## System Tests
System Test Plan
Test ID | Area | Priority | Owner Role | Description | Execution Steps | Expected Result | Result | Suggested Evidence
ST-001 | Deployment setup | Critical | Engineering | Setup notebook creates the target schema before table creation | Run the setup notebook against a clean test catalog/schema. Use CREATE SCHEMA IF NOT EXISTS before service.create_tables. | The schema exists and the notebook proceeds to table creation without manual pre-work. |  | Notebook run URL and SHOW SCHEMAS/SHOW DATABASES output.
ST-002 | Deployment setup | Critical | Engineering | Rules engine metadata tables are created with standard names | Instantiate RulesEngineService.from_schema with the target schema and call service.create_tables(mode='ignore'). | ruleset_versions and function_registry exist in the target schema. Rerunning the cell does not fail. |  | SHOW TABLES output and notebook rerun evidence.
ST-003 | Deployment setup | High | Engineering | Custom metadata table names are honored by the service | Instantiate RulesEngineService.from_schema with ruleset_versions_table and function_registry_table overrides, then create tables. | The custom tables are created and service.table_names reports the custom names for later publish/load calls. |  | Notebook output showing service.table_names and SHOW TABLES output.
ST-004 | Deployment setup | Critical | Engineering | Metadata table DDL preserves NOT NULL columns | After table creation, DESCRIBE TABLE EXTENDED or catalog inspection is run for both metadata tables. | Required columns such as ruleset_id, ruleset_name, version, status, effective_start_date, effective_end_date, payload_json, content_hash, rule_count, function_name, implementation_reference, and active_flag are marked NOT NULL where expected. |  | DESCRIBE TABLE output for both tables.
ST-005 | Deployment setup | High | Engineering | Overwrite mode is restricted to disposable environments | Run setup in a smoke/dev schema using mode='overwrite'. Verify project guidance blocks or avoids overwrite for production-like schemas. | Overwrite recreates tables only in disposable schemas. Production setup uses mode='ignore' or 'error'. |  | Notebook parameters and execution log.
ST-006 | Function registry | Critical | Engineering | Standard function metadata is registered after setup | Call service.save_standard_function_registry after table creation. | function_registry contains all package standard functions with expected implementation_reference, active_flag, allowed flags, return type, and version. |  | Query output ordered by function_name.
ST-007 | Function registry | High | Engineering | Standard function registration is rerunnable and skips existing functions | Run service.save_standard_function_registry twice without update_existing=True. | Second run succeeds and does not overwrite existing rows. Row count remains stable and existing metadata is preserved. |  | Before/after function_registry row counts and sample row values.
ST-008 | Function registry | Medium | Engineering | Explicit standard function metadata refresh can update existing rows | Run service.save_standard_function_registry(update_existing=True) in a controlled test schema. | Existing standard function rows are upserted without duplicates. Metadata remains valid after refresh. |  | MERGE/job output and post-refresh query.
ST-009 | Function registry | Critical | Engineering | Runtime in-memory registry contains executable standard implementations | Instantiate RulesEngineService.from_schema with default register_standard=True and inspect registry specs or run a ruleset using standard custom functions. | Standard functions are available for validation and runtime evaluation even though function_registry only stores metadata. |  | Notebook output showing successful validation/evaluation using a standard function.
ST-010 | Function registry | High | Engineering | Custom function metadata can be saved without breaking standard registry rows | Save a test custom FunctionRegistryRow through service.save_function_registry_rows. | The custom function row is inserted or updated and existing standard rows remain present. |  | function_registry query for standard and custom rows.
ST-011 | YAML compilation | Critical | Engineering | Valid canonical ruleset YAML compiles through the service | Call service.compile_yaml_path on a known good ruleset YAML artifact. | A Ruleset object is returned with expected ruleset_id, ruleset_name, version, owner, owner_department, rules, conditions, and assignments. |  | Notebook output showing compiled metadata and rule count.
ST-012 | YAML compilation | High | Engineering | YAML text compilation works for notebook-authored payloads | Call service.compile_yaml_text on a canonical YAML string. | The text compiles into the same model shape as file-based compilation. |  | Notebook output and compiled ruleset summary.
ST-013 | YAML compilation | High | Engineering | Unsupported legacy aliases are rejected clearly | Compile YAML using unsupported keys such as assignments or operand value. | Compilation fails with a clear message identifying the unsupported key and canonical replacement. |  | Expected exception output.
ST-014 | YAML compilation | Critical | Engineering | Required top-level ruleset metadata is enforced | Compile YAML missing ruleset_id, ruleset_name, version, or rules list. | Compilation fails before validation or persistence. Error identifies the missing or malformed field. |  | Expected exception output.
ST-015 | YAML compilation | High | Engineering | Condition group logical operator shape is enforced | Compile YAML with missing or multiple logical operator keys in a condition group. | Compilation fails and identifies that exactly one logical operator is required. |  | Expected exception output.
ST-016 | Semantic validation | Critical | Engineering | Valid simple row-level rule passes validation | Compile a simple ruleset using field/literal comparison and assignment, then run service.validator.validate. | Validation passes with no error-severity issues. |  | validation.to_text output.
ST-017 | Semantic validation | Critical | Engineering | Owner and owner_department are required before publish | Validate a ruleset missing owner or owner_department. | Validation returns error-severity issues and publish is blocked. |  | Validation output and failed publish evidence.
ST-018 | Semantic validation | High | Engineering | Duplicate condition_id values are rejected | Validate a ruleset with duplicate condition IDs across rules or nested groups. | Validation returns a duplicate condition ID error. |  | Validation output.
ST-019 | Semantic validation | High | Engineering | Duplicate condition_group_id values are rejected | Validate a ruleset with duplicate group IDs. | Validation returns a duplicate condition group ID error. |  | Validation output.
ST-020 | Semantic validation | Critical | Engineering | Aggregate scope rules are enforced | Validate aggregates where dataset scope includes by fields or group scope omits by fields. | Validation reports scope-specific aggregate errors. |  | Validation output.
ST-021 | Semantic validation | High | Engineering | Order-sensitive aggregates require order_by | Validate first/last aggregate without order_by. | Validation returns a clear order_by requirement error. |  | Validation output.
ST-022 | Semantic validation | High | Engineering | Aggregate filters reject nested aggregate operands | Validate a filtered aggregate whose filter predicate contains an aggregate operand. | Validation rejects the nested aggregate in the filter. |  | Validation output.
ST-023 | Semantic validation | High | Engineering | Operator arity and literal collection requirements are enforced | Validate operators such as is_null, between, in, and not_in with invalid right operands. | Validation identifies missing, extra, or malformed operands. |  | Validation output.
ST-024 | Semantic validation | Medium | Engineering | Null handling modes require default values when configured | Validate null_result_mode=default without null_default_value. | Validation returns a default-value requirement error. |  | Validation output.
ST-025 | Spark compatibility | Critical | Engineering | Spark validator accepts supported rulesets | Run SparkRulesetCompatibilityValidator through service.validator on representative supported rulesets. | Validation passes and no Spark-specific unsupported-operation issues are present. |  | Validation output.
ST-026 | Spark compatibility | High | Engineering | Spark validator rejects unsupported aggregate semantics | Validate rulesets using Spark-unsupported exact median, exact quantile, or aggregate null modes marked error. | Validation returns Spark compatibility errors before publish. |  | Validation output.
ST-027 | Publishing | Critical | Engineering | Publish YAML path compiles, normalizes, validates, and writes metadata | Call service.publish_yaml_path on a valid YAML artifact. | One published ruleset_versions row is written with status published, content_hash, payload_json, counts, owner, published_by, and published_at. |  | ruleset_versions query for the published row.
ST-028 | Publishing | Critical | Engineering | Direct publish of a compiled ruleset works | Compile YAML, validate it, then call service.publish(ruleset, published_by=...). | The compiled ruleset is persisted and loadable by name/version. |  | Notebook output and load_published confirmation.
ST-029 | Publishing | Critical | Engineering | Publish rejects non-published lifecycle status | Attempt to publish a compiled ruleset with status retired. | Publish fails before persistence with a clear status requirement message. |  | Expected exception output and unchanged table row count.
ST-030 | Publishing | Critical | Engineering | Duplicate ruleset_name and version cannot be published twice | Publish a ruleset, then attempt to publish another ruleset with the same ruleset_name and version. | Second publish fails and does not overwrite the original row. |  | Exception output and original row content_hash comparison.
ST-031 | Publishing | High | Engineering | Multiple published versions for the same ruleset_name are allowed | Publish version 1 and version 2 for the same ruleset_name. | Both rows have status published. Neither publish requires retiring the other version. |  | ruleset_versions query showing both versions.
ST-032 | Publishing | High | Engineering | Loading by name without version is rejected when ambiguous | With two published versions for the same ruleset_name, call service.load_published(ruleset_name) without version. | Repository raises an error asking the caller to specify version. |  | Expected exception output.
ST-033 | Publishing | Critical | Engineering | Loading by name and version reconstructs the canonical ruleset | Call service.load_published(ruleset_name, version) for a published row. | The returned Ruleset matches the published metadata and can be evaluated. |  | Notebook output comparing name, version, rule count, and content hash context.
ST-034 | Lifecycle | Critical | Engineering | Retirement makes a version unavailable to load_published | Publish a ruleset, call service.retire(ruleset_id, version), then attempt load_published by name/version. | The row status is retired and load_published no longer returns it. |  | ruleset_versions query and expected load failure.
ST-035 | Lifecycle | High | Engineering | Retirement stamps retired_by and retired_at | Retire a published version with retired_by populated. | retired_by and retired_at are populated and status is retired. |  | ruleset_versions lifecycle column output.
ST-036 | Lifecycle | High | Engineering | Retiring a missing ruleset version fails safely | Call service.retire for a ruleset_id/version that does not exist. | Repository raises a clear not-found error and no rows are changed. |  | Expected exception output.
ST-037 | Lifecycle | High | Engineering | Retiring an already retired version does not silently succeed | Retire a version, then attempt to retire it again. | Second retirement fails validation or status verification instead of silently succeeding. |  | Expected exception output.
ST-038 | Runtime Python | Critical | Engineering | Python runtime evaluates simple row-level rules correctly | Evaluate representative in-memory rows with a loaded ruleset using Python runtime service components. | Matched flags, matched rule IDs, assignments, traces, and errors match expected outcomes. |  | Actual vs expected output table.
ST-039 | Runtime Python | High | Engineering | Python runtime honors rule_order and stop_on_match | Evaluate rows where multiple rules can match and stop_on_match is configured. | Assignments reflect ordered evaluation and stop behavior. |  | Actual vs expected output table.
ST-040 | Runtime Python | High | Engineering | Python runtime applies null_input_mode and null_result_mode correctly | Evaluate rows containing null fields across propagate, false, true, error, default, and null modes where applicable. | Results match documented null semantics and errors are emitted only where expected. |  | Actual vs expected output table.
ST-041 | Runtime Python | High | Engineering | Python runtime evaluates aggregate operands correctly | Evaluate a ruleset with dataset and group aggregate operands over representative records. | Aggregate comparisons and assignments match manually calculated expected values. |  | Input data, expected calculations, and output table.
ST-042 | Runtime Spark | Critical | Engineering | Spark runtime evaluates a published ruleset against a DataFrame | Load a published ruleset by name/version and call service.evaluate_dataframe on a Spark DataFrame. | Output DataFrame contains matched, matched_rule_ids, assign, rule_results, and error columns with expected values. |  | Displayed output DataFrame and schema.
ST-043 | Runtime Spark | High | Engineering | Spark runtime fail_on_error behavior is enforced | Evaluate a ruleset/input combination that triggers a runtime error with fail_on_error=True and False. | fail_on_error=True fails the job. fail_on_error=False records errors in output rows. |  | Notebook output for both runs.
ST-044 | Runtime Spark | High | Engineering | Spark runtime supports standard custom functions used in rules | Publish and evaluate a ruleset that uses standard functions such as upper, trim, regex_extract, or to_number. | Evaluation succeeds and outputs match expected transformed values. |  | Actual vs expected output table.
ST-045 | Runtime Spark | Medium | Engineering | Spark and Python runtime outputs remain equivalent for shared supported cases | Run the same supported ruleset and input through Python and Spark runtimes. | Matched flags, assignments, and rule traces are equivalent after normalizing output representation. |  | Cross-runtime comparison table.
ST-046 | Auditability | Critical | Engineering | Payload JSON excludes mutable lifecycle fields and reconstructs ruleset content | Inspect payload_json for a published row and deserialize/load the row. | payload_json contains canonical ruleset content but not lifecycle status. Loading reconstructs the expected ruleset. |  | payload_json sample and load output.
ST-047 | Auditability | High | Engineering | Content hash is deterministic and reproducible | Publish or serialize the same ruleset content twice in a controlled test and recompute SHA-256 from payload_json. | content_hash is stable and equals SHA-256 of payload_json bytes. |  | Hash calculation output.
ST-048 | Auditability | Medium | Engineering | Summary count columns match the published ruleset content | Compare rule_count, condition_count, assignment_count, aggregate_count, and custom_function_count to the compiled ruleset. | Persisted counts match the model counts. |  | Query output and model count output.
ST-049 | Pipeline notebooks | Critical | Engineering | Publish notebook re-instantiates service against existing setup tables | Run notebook 2 after notebook 1 using the same schema or custom table parameters. | Notebook 2 compiles, validates, publishes, and verifies the ruleset without recreating setup objects. |  | Notebook 2 run URL and ruleset_versions query.
ST-050 | Pipeline notebooks | High | Engineering | Notebook verification checks are present after setup and publish | Review notebooks for assertions that tables exist, standard functions are registered, published row count equals one for target name/version, and load_published succeeds. | Both notebooks fail fast when expected deployment or publish verification conditions are not met. |  | Notebook source review and run output.

## UAT Tests
User Acceptance Test Plan
Test ID | Area | Priority | Owner Role | Plain-English Test Description | Execution Steps | Expected Result | Result | Suggested Evidence
UAT-001 | Business authoring | Critical | Business Owner | Business owner can identify the ruleset from YAML metadata | Open the ruleset YAML or notebook summary and review ruleset name, version, owner, department, and description. | Metadata matches the intended business rule set and release candidate. |  | Business confirmation notes or screenshot.
UAT-002 | Business authoring | Critical | Business Owner | Rules listed in YAML match approved business scenarios | Review the rule names, descriptions, order, and plain-English conditions for the release candidate. | Rules correspond to approved business logic and no expected rule is missing. |  | Marked-up YAML or review notes.
UAT-003 | Business authoring | High | Business Owner | Assignments produced by matching rules are business-meaningful | Review target fields and assigned values for each rule. | Assignment fields and values match business expectations and downstream consumers understand them. |  | Assignment review checklist.
UAT-004 | Business authoring | High | Business Owner | Rule order and stop-on-match behavior match business priority | Review scenarios where multiple rules could match the same record. | The chosen rule order and stop behavior produce the intended winning assignment. |  | Scenario notes and expected outcome table.
UAT-005 | Validation messaging | High | UAT Tester | Validation errors are understandable to a non-engineering rule author | Run validation against an intentionally invalid ruleset and review the output. | The message identifies what is wrong and where the author should fix the YAML. |  | Tester comments on error clarity.
UAT-006 | Publish readiness | Critical | Business Owner | Validated release candidate can be approved for publishing | Run compile and validation on the candidate ruleset. | No blocking errors are present. Any warnings are reviewed and accepted before publish. |  | Validation output and approval note.
UAT-007 | Publish readiness | Critical | Business Owner | Published version is visible and identifiable in metadata | After publish, review the ruleset_versions row for the candidate. | Business owner can see the expected ruleset_name, version, status, owner, published_by, and published_at. |  | Published metadata screenshot.
UAT-008 | Version testing | High | Business Owner | Multiple published versions can coexist for comparison testing | Publish current and candidate versions for the same ruleset_name in UAT. | Both versions are visible and testers can choose the intended version explicitly. |  | ruleset_versions screenshot showing both versions.
UAT-009 | Version testing | High | UAT Tester | Testers understand that version is required when multiple published versions exist | Attempt to load by name only when multiple versions are published, then load by explicit version. | Name-only load reports ambiguity. Explicit version load succeeds. |  | Notebook output.
UAT-010 | Runtime results | Critical | Business Owner | Representative business records receive expected rule outcomes | Run the published ruleset against a curated UAT input dataset. | Each sampled record has expected matched status, matched rule, and assignment output. |  | Actual vs expected UAT results workbook/table.
UAT-011 | Runtime results | Critical | Business Owner | Non-matching records remain unassigned or assigned as expected | Include records that should not match any rule or should follow default behavior. | Outputs match the intended non-match behavior without unexpected assignments. |  | Actual vs expected output table.
UAT-012 | Runtime results | High | Business Owner | Boundary values produce expected outcomes | Test thresholds, equality edges, nulls, blanks, and representative text/case variations. | Boundary records follow approved business semantics. |  | Boundary scenario result table.
UAT-013 | Runtime results | High | Business Owner | Aggregate-based business rules match manual calculations | For rules using group or dataset aggregates, compare engine outputs to manually reviewed aggregate calculations. | Engine results agree with manual calculations for sampled groups or datasets. |  | Manual calculation sheet and output screenshot.
UAT-014 | Custom functions | Medium | Business Owner | Standard text/number transformations produce recognizable business outcomes | Review rules using functions such as trim, upper, regex_extract, or to_number on representative records. | Function-driven outcomes match what business users expect from the source data. |  | Before/after sample output.
UAT-015 | Operational workflow | High | UAT Tester | Setup notebook can be rerun safely before publishing | Rerun setup notebook after tables and function metadata already exist. | Notebook succeeds and does not duplicate or overwrite standard function metadata unexpectedly. |  | Notebook rerun output and function count comparison.
UAT-016 | Operational workflow | High | UAT Tester | Publish notebook can be rerun safely for same candidate and handles duplicate publish clearly | Rerun publish notebook for an already-published ruleset_name/version. | Notebook fails or stops with a clear duplicate version message and does not overwrite the original published row. |  | Notebook output and original row evidence.
UAT-017 | Operational workflow | High | Release Manager | Retirement workflow removes a version from runtime eligibility | Retire a test version that should no longer be used. | The version status changes to retired and cannot be loaded through published-only load calls. |  | Lifecycle row screenshot and load failure output.
UAT-018 | Operational workflow | Medium | Release Manager | Release evidence is sufficient for audit review | Review publish metadata, content hash, payload_json availability, validation output, and notebook run links. | Release evidence is complete enough to support approval and later audit. |  | Evidence package checklist.
UAT-019 | Downstream readiness | High | Data Consumer | Output DataFrame schema is usable by downstream jobs | Review Spark runtime output columns with a downstream consumer or integration owner. | Column names, JSON fields, matched flags, and error field are understood and usable. |  | Consumer sign-off notes.
UAT-020 | Downstream readiness | High | Data Consumer | Assignment JSON can be parsed by downstream Spark consumers | Parse the assign output using downstream expected schema or from_json logic. | Assignments can be parsed and consumed without manual cleanup. |  | Parsed output screenshot.
UAT-021 | Exception handling | Medium | UAT Tester | Runtime error handling is acceptable for business operations | Review behavior when fail_on_error is true and false using a controlled bad input scenario. | The team agrees which mode is appropriate for production and how errors will be monitored. |  | Decision notes.
UAT-022 | Documentation | Medium | UAT Tester | Notebook instructions are clear enough for a new operator | Ask a tester who did not write the notebooks to run setup and publish in UAT. | Tester can complete the process using notebook instructions and parameters without engineering intervention. |  | Tester feedback.
UAT-023 | Sign-off | Critical | Business Owner | Business owner approves the published candidate version | Review validation output, UAT outputs, and open defects. | Business owner records approve/defer/reject decision with comments. |  | Sign-Off tab entry or approval reference.
UAT-024 | Sign-off | Critical | Release Manager | Release manager confirms deployment readiness | Review system test status, UAT status, defect disposition, and rollback/retirement plan. | Release manager signs off or records conditions for release. |  | Sign-Off tab entry or release approval link.

## Results Log
Test Execution Results Log
Result ID | Test ID | Test Type | Execution Date | Tester Name | Environment | Result | Actual Outcome | Evidence Location | Defect ID | Retest Required? | Reviewer Notes
R-001 | [5 empty] | Not Run
R-002 | [5 empty] | Not Run
R-003 | [5 empty] | Not Run
R-004 | [5 empty] | Not Run
R-005 | [5 empty] | Not Run
R-006 | [5 empty] | Not Run
R-007 | [5 empty] | Not Run
R-008 | [5 empty] | Not Run
R-009 | [5 empty] | Not Run
R-010 | [5 empty] | Not Run
R-011 | [5 empty] | Not Run
R-012 | [5 empty] | Not Run
R-013 | [5 empty] | Not Run
R-014 | [5 empty] | Not Run
R-015 | [5 empty] | Not Run
R-016 | [5 empty] | Not Run
R-017 | [5 empty] | Not Run
R-018 | [5 empty] | Not Run
R-019 | [5 empty] | Not Run
R-020 | [5 empty] | Not Run
R-021 | [5 empty] | Not Run
R-022 | [5 empty] | Not Run
R-023 | [5 empty] | Not Run
R-024 | [5 empty] | Not Run
R-025 | [5 empty] | Not Run
R-026 | [5 empty] | Not Run
R-027 | [5 empty] | Not Run
R-028 | [5 empty] | Not Run
R-029 | [5 empty] | Not Run
R-030 | [5 empty] | Not Run
R-031 | [5 empty] | Not Run
R-032 | [5 empty] | Not Run
R-033 | [5 empty] | Not Run
R-034 | [5 empty] | Not Run
R-035 | [5 empty] | Not Run
R-036 | [5 empty] | Not Run
R-037 | [5 empty] | Not Run
R-038 | [5 empty] | Not Run
R-039 | [5 empty] | Not Run
R-040 | [5 empty] | Not Run
R-041 | [5 empty] | Not Run
R-042 | [5 empty] | Not Run
R-043 | [5 empty] | Not Run
R-044 | [5 empty] | Not Run
R-045 | [5 empty] | Not Run
R-046 | [5 empty] | Not Run
R-047 | [5 empty] | Not Run
R-048 | [5 empty] | Not Run
R-049 | [5 empty] | Not Run
R-050 | [5 empty] | Not Run
R-051 | [5 empty] | Not Run
R-052 | [5 empty] | Not Run
R-053 | [5 empty] | Not Run
R-054 | [5 empty] | Not Run
R-055 | [5 empty] | Not Run
R-056 | [5 empty] | Not Run
R-057 | [5 empty] | Not Run
R-058 | [5 empty] | Not Run
R-059 | [5 empty] | Not Run
R-060 | [5 empty] | Not Run
R-061 | [5 empty] | Not Run
R-062 | [5 empty] | Not Run
R-063 | [5 empty] | Not Run
R-064 | [5 empty] | Not Run
R-065 | [5 empty] | Not Run
R-066 | [5 empty] | Not Run
R-067 | [5 empty] | Not Run
R-068 | [5 empty] | Not Run
R-069 | [5 empty] | Not Run
R-070 | [5 empty] | Not Run
R-071 | [5 empty] | Not Run
R-072 | [5 empty] | Not Run
R-073 | [5 empty] | Not Run
R-074 | [5 empty] | Not Run
R-075 | [5 empty] | Not Run
R-076 | [5 empty] | Not Run
R-077 | [5 empty] | Not Run
R-078 | [5 empty] | Not Run
R-079 | [5 empty] | Not Run
R-080 | [5 empty] | Not Run
R-081 | [5 empty] | Not Run
R-082 | [5 empty] | Not Run
R-083 | [5 empty] | Not Run
R-084 | [5 empty] | Not Run
R-085 | [5 empty] | Not Run
R-086 | [5 empty] | Not Run
R-087 | [5 empty] | Not Run
R-088 | [5 empty] | Not Run
R-089 | [5 empty] | Not Run
R-090 | [5 empty] | Not Run
R-091 | [5 empty] | Not Run
R-092 | [5 empty] | Not Run
R-093 | [5 empty] | Not Run
R-094 | [5 empty] | Not Run
R-095 | [5 empty] | Not Run
R-096 | [5 empty] | Not Run
R-097 | [5 empty] | Not Run
R-098 | [5 empty] | Not Run
R-099 | [5 empty] | Not Run
R-100 | [5 empty] | Not Run
R-101 | [5 empty] | Not Run
R-102 | [5 empty] | Not Run
R-103 | [5 empty] | Not Run
R-104 | [5 empty] | Not Run
R-105 | [5 empty] | Not Run
R-106 | [5 empty] | Not Run
R-107 | [5 empty] | Not Run
R-108 | [5 empty] | Not Run
R-109 | [5 empty] | Not Run
R-110 | [5 empty] | Not Run
R-111 | [5 empty] | Not Run
R-112 | [5 empty] | Not Run
R-113 | [5 empty] | Not Run
R-114 | [5 empty] | Not Run
R-115 | [5 empty] | Not Run
R-116 | [5 empty] | Not Run
R-117 | [5 empty] | Not Run
R-118 | [5 empty] | Not Run
R-119 | [5 empty] | Not Run
R-120 | [5 empty] | Not Run
R-121 | [5 empty] | Not Run
R-122 | [5 empty] | Not Run
R-123 | [5 empty] | Not Run
R-124 | [5 empty] | Not Run
R-125 | [5 empty] | Not Run
R-126 | [5 empty] | Not Run
R-127 | [5 empty] | Not Run
R-128 | [5 empty] | Not Run
R-129 | [5 empty] | Not Run
R-130 | [5 empty] | Not Run
R-131 | [5 empty] | Not Run
R-132 | [5 empty] | Not Run
R-133 | [5 empty] | Not Run
R-134 | [5 empty] | Not Run
R-135 | [5 empty] | Not Run
R-136 | [5 empty] | Not Run
R-137 | [5 empty] | Not Run
R-138 | [5 empty] | Not Run
R-139 | [5 empty] | Not Run
R-140 | [5 empty] | Not Run
R-141 | [5 empty] | Not Run
R-142 | [5 empty] | Not Run
R-143 | [5 empty] | Not Run
R-144 | [5 empty] | Not Run
R-145 | [5 empty] | Not Run
R-146 | [5 empty] | Not Run
R-147 | [5 empty] | Not Run
R-148 | [5 empty] | Not Run
R-149 | [5 empty] | Not Run
R-150 | [5 empty] | Not Run
R-151 | [5 empty] | Not Run
R-152 | [5 empty] | Not Run
R-153 | [5 empty] | Not Run
R-154 | [5 empty] | Not Run
R-155 | [5 empty] | Not Run
R-156 | [5 empty] | Not Run
R-157 | [5 empty] | Not Run
R-158 | [5 empty] | Not Run
R-159 | [5 empty] | Not Run
R-160 | [5 empty] | Not Run
R-161 | [5 empty] | Not Run
R-162 | [5 empty] | Not Run
R-163 | [5 empty] | Not Run
R-164 | [5 empty] | Not Run
R-165 | [5 empty] | Not Run
R-166 | [5 empty] | Not Run
R-167 | [5 empty] | Not Run
R-168 | [5 empty] | Not Run
R-169 | [5 empty] | Not Run
R-170 | [5 empty] | Not Run
R-171 | [5 empty] | Not Run
R-172 | [5 empty] | Not Run
R-173 | [5 empty] | Not Run
R-174 | [5 empty] | Not Run
R-175 | [5 empty] | Not Run
R-176 | [5 empty] | Not Run
R-177 | [5 empty] | Not Run
R-178 | [5 empty] | Not Run
R-179 | [5 empty] | Not Run
R-180 | [5 empty] | Not Run
R-181 | [5 empty] | Not Run
R-182 | [5 empty] | Not Run
R-183 | [5 empty] | Not Run
R-184 | [5 empty] | Not Run
R-185 | [5 empty] | Not Run
R-186 | [5 empty] | Not Run
R-187 | [5 empty] | Not Run
R-188 | [5 empty] | Not Run
R-189 | [5 empty] | Not Run
R-190 | [5 empty] | Not Run
R-191 | [5 empty] | Not Run
R-192 | [5 empty] | Not Run
R-193 | [5 empty] | Not Run
R-194 | [5 empty] | Not Run
R-195 | [5 empty] | Not Run
R-196 | [5 empty] | Not Run
R-197 | [5 empty] | Not Run
R-198 | [5 empty] | Not Run
R-199 | [5 empty] | Not Run
R-200 | [5 empty] | Not Run

## Defect Log
Defect Log
Defect ID | Related Test ID | Severity | Reported Date | Reported By | Plain-English Defect Summary | Business Impact | Status | Owner | Resolution Notes
D-001
D-002
D-003
D-004
D-005
D-006
D-007
D-008
D-009
D-010
D-011
D-012
D-013
D-014
D-015
D-016
D-017
D-018
D-019
D-020
D-021
D-022
D-023
D-024
D-025
D-026
D-027
D-028
D-029
D-030
D-031
D-032
D-033
D-034
D-035
D-036
D-037
D-038
D-039
D-040
D-041
D-042
D-043
D-044
D-045
D-046
D-047
D-048
D-049
D-050
D-051
D-052
D-053
D-054
D-055
D-056
D-057
D-058
D-059
D-060
D-061
D-062
D-063
D-064
D-065
D-066
D-067
D-068
D-069
D-070
D-071
D-072
D-073
D-074
D-075
D-076
D-077
D-078
D-079
D-080
D-081
D-082
D-083
D-084
D-085
D-086
D-087
D-088
D-089
D-090
D-091
D-092
D-093
D-094
D-095
D-096
D-097
D-098
D-099
D-100

## Sign-Off
UAT and Release Sign-Off
Role | Name | Decision | Date | Comments / Conditions | Signature or Approval Reference
Business Owner
Engineering Lead
Data Engineering Owner
Rules Authoring Owner
QA / UAT Coordinator
Release Manager
Operations Support Owner